## Website Rebrand
TPG Website Rebrand Framework and Plan |  |  | Priority | External POC | Owner | Contributors | Status | Note | Dependency | ETA | Area | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Week 13 | Week 14 | Week 15 | Week 16 | Week 17 | Week 18 | Week 19 | Week 20 | Week 21 | Week 22 | Week 23 | Week 24 | Week 25 | Week 26 | Week 27 | Week 28 | Week 29 | Week 30 | Week 31 | Week 32 | Week 33 | Week 34 | Week 35
Website Rebrand
Strategic Planning and Stakeholder Communications
Setup Initial Project Plan Framework with Key initiatives, milestones, and target timelines
Identify Project Specifications and evaluate estimated resource requirements
Determine MVP, Phases, and what is included in initial launch plan
Kickoff Project, review project goals, costs, and timelines, overview, and target ETAs
Determine and Document Stakeholder inputs, and approval processes, and communicate to involved parties
Allocate cross-functional Support Resources (Customer Success, Sales, Prod, Services,)
Begin Website Partner and technology scoping and evaluation processes
Surface 2-3 solutions candidates and evaluate pros/cons. Select best candidates.
Tech Functional Marketing Capabilities
Tech Accessibility Capability Analysis
Mar-tech Stack/Integrations (HS, SF, Tend, GA, etc...)
Ongoing Support, Mainintenance, updates capabilities
Evaluate Partner Exerience, expertise, track-record
Partner and Technology Selection and Contracting
Project Plan Update & Resource Assigns
Content & Information Architecture
Brainstorming Meeting - Gather and organize Ideas, Needs assessments
Sitemap & Architecture Diagrams - Create V1 and work with vendor to finalize
Templates identified to meet architecture requirements (quantity and types)
Content inventory audit -
Map content for migration and new content creation requirements
Produce page level Kanban-production tracker for prototype, content, graphics, accessibility, approvals
Map Ecommerce Integration capabilities for self-serve premium content and subscriptions
Map and document Trial processes and primary site CTAs
Finalize architecture with vendor
Brand Definitions
Visual Identity documentation - logo, colors, fonts, photography, illustration, icons
UX review of visual identity
Verbal Identity - Messaging, positioning, major value props, taglines, tone,
Brand Style Guidelines - Updates
Accessibility review of guidelines (work in partnership with Dave G. )
Design Comps and Creative Builds
Homepage layout, wireframes, and design mockups -
Primary Navigation Design
UX Inclusive Design Review sessions, feedback and recommendations
Product Detail Page - Page Flow & Layout Design
Page Element Designs - component specs
Page Template wireframes, design, for remaining undefined templates
Setup Content templates in Google doc for content production/migration for each template
HTML/CSS Widget Identification for Accessible Code library
Registration Litebox, fields, User Flow
Ecommerce visual design,cart, checkouts, confirmation
Marketing Design Review Session (for each template or major component)
Ux touch-points throughout - even if quick yes/no or elements
usability testing - user journey or site
Design Iterations and Adjustments (Collaborative reviews)
Design Review & Approval Meetings (primary design direction)
Website Development - Technical Builds
Setup technical environments, staging, dev, and create content access, permissions
Functional Template Build Plan (See kanban project tracking)
Header
Navigation
Component - Flex Module
Template 1 - Homepage
Template 2 - Products Listing/Overview
Template 3 - Product Detail
Template 4 - Services Overview
Template 5 - Services Listing
Template 6 - About, Contact,
Template 7 - resources Overview
Template 8 - Resources Details, SEO content pages,
Template 9 - Campaign Landing Page,
CTAs and Form technical implementations
Build accessible code library for common "widget" (2 column, 3 column, accordian, slider, etc..)
Ecommerce Systems Integrations and Development (if part of MVP
Accessibility Reviews and technical updates
Business Blog
Determine technology (Wordpress, or other platform)
Design Listing Page layout,
Design single page layout, CTAs, and other integrations
Developement/coding to acheive requirements
Accessibility Review
Coding Headers/footers, these selection, editor selection
Migrate content - if manual process, may take longer
Website Content Production and Migration
editorial guidelines
Organize Overall Messaging definitions and creation (content for use on website, banners, syndication)
populate messaging templates (defined above) for each target page
Imagery creation and selection for pages (graphics, images, videos, etc..)
SEO Content Page Definitions - keyword targeting 3-5 pages)
SEO content page content builds
Content creation and approvals for all pages on website in G docs
Transfer content into CMS template pages
Content Approvals and iterative improvements
Social message planning
Form and MA / Hubspot Setup & Configuration
Email campagin definitions and planning
Audience segmentation and workflow design, configuration, and scheduling
Email template & message creation and build.3-4 unique distributions, welcome, follow-up, upsell, etc…
Email template design review
Establish lead scoring and configure baseline scoring (sessions, usage, key actions)
Email content review and approvals , testing, and Marketing QA.
Integrate with SF, establish common fields, push and sync definitions, write
Forms definitions, setup, and integration (API versus native forms?)
Lead Flow QA and validation
Analytics & Tags Setup and Configuration
Define GA technical tracking requirements (GTM vs GA base code, methods, customizations)
Code the custom JS snippets, add any other tracking requirements (crazyegg, tend, adwords, FB, Twitter codes)
Custom User Flow and goal tracking setup and configuration
Attribution testing and validation - GA, SF, HS, Tend
Staging QA and Release Validation
Accessiblity AA success criteria validation
Setup and run ARC to set initial baselines and identify any immediate issues
Accessibility issue resolutions (Launch Critical Items)
Marketing QA - copy, imagery, user flows
Forms QA (templates including campaigns, products, SEO, resources, etc..
QA Issue resolutions
Final Launch Approval
Product Launch

## Roles
Roles | Description | Owner | Contributors | Notes
Overall Project Lead | Ensure successful delivery of unified brand across the organization. (Clear communications,
Website Rebrand | Ensure delivery of new rebranded website (new tech, design, messaging, infrastructure, partner, lead-collection, templates,
Cross-Functional Rebrand | Project Manage execution of cross-functional rebrand efforts
SalesForce Rebrand | Rebrand documentation, updating integrations, align processes to unified methodoligies
Accessibilty Engineer | Assist in technical evaluations, QA, accessible coding/html practices/recommendations, and AA compliance approval |  |  | Work to monitor/manage both Production/Dev environments through ARC, Setup call wiht Hans to discuss his input on this. Give access to TPG tutor - checklist, and other resources to dev agency.
Legal | Updating legal documents, Trademark registration, other DBA, & Legal items
Brand Style-Guide | Updating style-guide and ensuring consistency in usage across TPG ARC |  |  | Matt Feldman created previous PDF version, have requested access to design files to make updates
SEO Strategy | Ensure website is optimized for search
Design | Identity, graphics creation, page design support (individual creative assets) |  |  | Will hire graphic designer -
UX | Consulting on wireframes/page layout for inclusive design |  |  | Email David Lerch - Don't add Henny to kickoff, wait until Dave Lerch who he wants
Analytics & Lead Flow | Installation of digital analytics, marketing automation system, lead capture, attribution, and lead flow processes
Messaging | Creation, Coordination, Editing, and populating content blocks
Blogs - Developer & WP Support | Align rebrand across developer resources, content, nav updates, templates, etc... |  |  | adrian - lead/ownership of dev content, framework, templates, forms, managed by marketing group, Goal - One blog, owned by Marcom
HR | Updating employee handbooks, materials, job descriptions, Internal launch party/planning
IT | Email Exchange Server updates, DNS configurations, |  |  | Ed - IT Director for Vispero, poten
Sales Stakeholder | Review sales related deliverables and provide feedback
SaaS Stakeholder | Review SaaS related deliverables and provide information, feedback, QA, and various approvals
Services Stakeholder | Review Services related deliverables and provide information, feedback, QA, and various approvals |  |  | Travis to discuss business needs for resources
Executive Stakeholder | Strategic inputs, final delivery approvals upon completion of QA releases
Launch Campaigns | Organizing and delivering successful launch campaigns (customer communications, webinar, PR)

## Rebrand General
TPG Rebrand Framework and Plan | Priority | Owner | Contributors | ETA | Status | Sequence | Note | Dependency | EST. | Area | Jan | Jan | Jan | Jan | Feb | Feb | Feb | Feb | Mar | Mar | Mar | Mar | Apr | Apr | Apr | Apr | May | MayMay | May | May | June | June | June | June | July | July | July | July | Aug | Aug | Aug | Aug | Sep | Sep | Sep | Sep | Oct | Oct | Oct | Estimated ETA: | Notes:
New Logo Delivery for updating internal SF and sales docs,
Employee Internal rebrand schwag purchase and distributed
Phone system updates - voice messaging
Update all instances of "Old Prodcut Name" to "New Product Name" -including changing logo on marketing elements and TPG Tutor product itself
Update internal wiki with new branding elements
Rebrand in videos we need to continue use of
Update Business Credit Cards
Internal time management branding updates
Create and disseminate new email signature
Update Zoom webinar page
Social media handles / Twitter
Application Login website updates - branding, links,
employee Handbook
Update content marketing site to new Wordpress framework
Blog style updates, navigation, links, domain migration, redirects, analytics
Setup new email addresses and implement email forwarding, signature updates
Update CRM documents, invoices, contracts, and other critical sales documents
Salesforce Domain configuration updates to new domain
conference backdrops, standups, handouts, and other schwag
powerpoint deck template (sales decks, conference decks, internal presentations)
Public One sheets - Primary marketing sheets update with new messaging
Updates to corporate site with new logo
Branding/logo updates and partner websites links to new domains
Establish trial / Free account process for self-serve with SaaS team, how it integrates, HS integration, workflows, segments
Integration of self-serve ecommerce into SaaS team,(pricing for website, process starts, etc... )
Domain DNS server configuration updates

## Components Kanban
Item | Owner | Dev Prototype | A11y Review | Remediation | Retested | Notes:
Header - nav, utility, | Brad | Ready for testing | Reviewed (issues found) | Complete | Approved | Tracking the issues in a separate sharable location with the developers. Multiple options including shareable docs, user stories, ARC Engagements, etc..
Primary Top Navigation
Global Alert Bar component
Utility Navigation
In-page Navigation
Hero Component
Icon Component
Flex Component
Gallery Component
Pricing Component
Global Contact Form Component
ACF Forms module
Accordion Component
Related Cards Component
Search Results Page
Footer
Content Creation Side - WP UI

## Page Level Kanban
Page/template | Owner | content blocks | Wireframe | Prototype | A11y QA | Product Page content | MKT QA | Content SME QA ETA () | SME QA done? 1/15 -20 | Graphics ETA( ) | Staging URL ETA () | Staging Status ETA () | mobile flow Testing | Form tested for Source and Submission | Accessibility QA | Ready for Launch 2/12 | Notes | document URLs
Homepage | Brad | Link to doc | Done | Done | Done | Done | Done | Done |  | Done | Done | Date Approved | Done | Done | Done | Done | enter notes and annotations
About
Contact
Get Help Overview
Product / Services Overview
Product Overview
Services Overview
Product Detail Pages
Product 1 | Brad | URL | URL | Approved | Complete | URL | Approved | Approved |  | Approved | URL | Approved | Approved | Approved | Approved | Approved
Product 2
Product 3
Product 4
Other pages
Tertiary Product 1
Tertiary Product 2
Solutions Detail Pages
Solutions 1
Solutions 2
Solutions 3
Solutions by Org Size (detail template)
Enterprise Business
SMB Solutions
Mid-Market Solutions
Resources
Hub Content Overview Page
Cornerstone Content 1
Cornerstone Content 2
Detail level Spoke Content 1
Detail level Spoke Content 2
Other Page Types
About us Page Types
Careers
Campaign Pages
PPC Landing Page 1
SEO Landing Page 2

## Final Stretch
Date | Checkpoints | Owner | Status | dependency | Note
2021-01-20 |  |  | done
2021-01-20
2021-01-20
2021-01-21
2021-01-21
2021-01-22
2021-01-25
2021-01-27
2021-01-25
2021-01-25
2021-01-28
2021-01-28
2021-02-01
2021-02-01
2021-02-01
2021-02-02
2021-02-02
2021-02-05
2021-02-10
2021-02-05
2021-02-10
2021-02-09
2021-02-08
2021-02-08
2021-02-08
2021-02-08
2021-02-08
2021-02-09
2021-02-12
2021-02-10
2021-02-09
2021-02-09
2021-02-10
2021-02-10
2021-02-10
2021-02-10
2021-02-10
2021-02-19
2021-02-12
2021-02-12
2021-02-13
2021-02-13
2021-02-13
2021-02-13
2021-02-15
2021-02-15
2021-02-15
Final Call to Proceed (T minus 4 business days)
2021-02-18
2021-02-18
2021-02-18
2021-02-18
2021-02-19
2021-02-19
2021-02-19
2021-02-19
2021-02-19
2021-02-16
2021-02-19
2021-02-19
2021-02-21 | Final Day Before Launch
7:00pm
8:00pm
7:00pm
2021-02-22 | Launch Day Tasks
7:00am
7:30am
9:00am
9:15am
9:30am
9:30am
9:30am
9:30am
9:45am
12:00pm
1:00pm
2021-02-23 | Post Launch Tasks
2021-02-25
2021-02-28

## MVP Definitions
Website Phase 1, MVP
Updated Style Guide and visual branding (logo, favicon, etc…)
New Product and Services Templates - Product Pages
Integration of Marketing Automation APIs
New Domain Migration
Implementation of redirects
Utility Navigation
Primary Navigation
new Footer
Resources Overview Hub page
New Resources tempates for Hub contents
Persona/Role based Information
WCAG AA compliance
Content marketing website Updates
Salesforce Documentation Updates
New exchange emails
Internal Launch employee branding
Updating blog with new corporate identify
Phase 2+ initiatives

## Estimates (hidden)
Deliverable | Estimate | Actual | Variance | Notes
Branding, Logo, Assets
Marketing Website
Design, graphics, & Assets |  |  |  | hero graphics, product visualizations, asset updates
TPGI Blog Synchronization |  |  |  | Adrian or some other agency?
IA website
New Conference Materials
External Launch Campaigns
Internal Branding Launch Items |  |  |  | 0 | per employee (100)
Sub-Total

## Project notes (hidden)
Notes:
2/1 - Delayed Kickoff nearly two weeks due to offsite executive meetings. Travis needed to get buy-in for announcing rebrand and for assignment of cross-functional resources
2/7 First week in Feb, Kathy/Travis added a significant new deliverable for the sales kickoff. Needed to create new product sheets and packaging sheets for the kickoff. Required shifting focus away from rebrand over that week.
2/10 2nd week in feb, Had to organize first presentation for company and launch the API product page. also had to focus time on hubspot account configuration for new domain and teams. Could not focus on rebrand deliverables.